## RAH Testing
RAH Testing - Traceability Matrix
Requirement | [7 empty] | UNIT TESTING |  |  | WORKSTREAM TESTING | [12 empty] | PROGRAMME SIT
[30 empty] | DAY2 CYCLE 12 RUN | [8 empty] | DAY2 CYCLE 13 RUN
S/N | Epic JIRA Ref # | Epic Description | BRD Ref# | Story JIRA Ref# | Story Description | FRD Ref# | Day 2 | Test Case Count | Test Results Available (Y/N) | Comments | Scenario JIRA Ref# | Gherkin Script Created (Y / N) | Automation (Y / N) | Automation Target Completion | Test Case Count | Tests Passed | Tests Failed | Tests Blocked | Tests Not Started | Tests Deferred | Defects Encountered | Test Results Sign Off Date | Comments | Test Scope Item | Program SIT Scenario Ref | Scenario JIRA Ref# | Gherkin Script Created (Y / N) | Automation (Y / N) | Automation Target Completion | Test Case Count | Tests Passed | Tests Failed | Tests Blocked | Tests Not Started | Tests Deferred | Defects Encountered | Test Results Sign Off Date | Comments | Test Case Count | Tests Passed | Tests Failed | Tests Blocked | Tests Not Started | Tests Deferred | Defects Encountered | Test Results Sign Off Date | Comments
1 | RFIFRS-49444 | Accounted exposure balances with accounting classification for ECL calculation | IFRS 9 EDM BRD v1 13 Scope 1 2.docx -2.2 Scope Statement | RFIFRS-49445 | 1) Sourcing of TP balances with (or without) GL chartfields at the granular level (trade/position/loan/card) 2) IFRS 9 classification (using Trade data attributes, portfolio mapping) 3) IFRS9 classification using COA chartfield 4) Reconciliation between two methods 5) Exposure accounting categorisation stamping 6) Exposure views and other assets, Charge off views 7) Detail row level Reporting views | Rubicon - IFRS 9 EDM BSD v0.4.docx - 3. The Solution | Day 2 | NA | Y | Refer to link in comment | [13 empty] | Accounting classification tagging for all inbound trades, Exosure accounting categorisation tagging for trades and Accounted balances by source views available in RAH T3 for extraction to ECL | IFRS 9 Classification & Measurement Compliance IFRS 9 Group ECL Accounting | RFIFRS-50544 |  |  |  | 83 | 83 | 0 | 0 | 0 | 0 | 0 |  | EDM to RAH row count check for NON FM Data ( TP: KEDW,EBBS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | EDM to RAH row count check for NON FM Data
[11 empty] | RFIFRS-49449 | [14 empty] | RFIFRS-49449 |  |  |  | 487 | 487 | 0 | 0 | 0 | 0 | 0 |  | Control-M jobs run: - Prepare ECL views (Trade, ASL Categorization) TP: EBBS,KEDW -Hadoop job for TP: KEDW ,EBBS -Recon jobs for TP: KEDW ,EBBS | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Control-M jobs run: - Day2 job related to processing Trade, ASL categ, GLSRC view TP:
[11 empty] | RFIFRS-49450 | [14 empty] | RFIFRS-49450 |  |  |  | 14 | 14 | 0 | 0 | 0 | 0 | 0 |  | Row count validation for tables inserted with data after job run TP: EBBS,KEDW | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Row count validation for tables inserted with data after job run TP:
[26 empty] | RFIFRS-50037 | Y | N | N/A | 16 | 16 | 0 | 0 | 0 | 0 | 0 |  | EDM pull data from RAH and load to PT tables. Duplicate check failed for TRADE & CLASS_ASL_CATEG - RFIFRS-60276 (Defer to next cycle) | 20 | 11 | 1 | 0 | 8 | 0 | 0 |  | EDM pull data from RAH and load to PT tables. Duplicate check failed for TRADE & CLASS_ASL_CATEG - RFIFRS-60276 (Retested and Pass) Duplicate check failed for ECL_GL_SOURCE - RFIFRS-60367
[26 empty] | RFIFRS-50038 | Y | N | N/A | 12 | 12 | 0 | 0 | 0 | 0 | 0 |  | EDM verify T1-T2-T3 mapping | 15 | 9 | 0 | 0 | 6 | 0 | 0 |  | EDM verify T1-T2-T3 mapping
[26 empty] | RFIFRS-50039 | Y | N | N/A | 4 | 4 | 0 | 0 | 0 | 0 | 0 |  | EDM pull data from ECL and load to PT tables.. | 4 | 0 | 0 | 0 | 4 | 0 | 0 |  | EDM pull data from ECL and load to PT tables.
2 | RFIFRS-49462 | Reconciliation Framework – TP GL reconciliation for the systems requiring financial reconciliation, Reconciliation between points of data transfers. | IFRS 9 EDM BRD v1 13 Scope 1 2.docx -2.2 Scope Statement | RFIFRS-49465 | 1) Reconciliation framework – to recon TP balances with Sourcewise ledger and preparation of datasets for consumption by ECL. | Rubicon - IFRS 9 EDM BSD v0.4.docx - 3. The Solution | Day 2 | NA | Y | Refer to link in comment | N/A- Covered off by Test Scenario RFIFRS-49449 | [12 empty] | GL Reconciliation : Reconciliation Framework – TP GL reconciliation for the systems that require stamping in RAH Reconciliation Framework – TP GL reconciliation for the systems with Chartfield Stamping already provided | IFRS 9 GL Reconciliation | N/A- Covered off by Test Scenario RFIFRS-49449 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Tested with the job run in RFIFRS-49449 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Tested with the job run in RFIFRS-49449
3 | RFIFRS-49456 | ECL feed to RAH containing provision data and stage information | IFRS 9 EDM BRD v1 13 Scope 1 2.docx -2.2 Scope Statement | RFIFRS-49457 | 1) ECL writeback to RAH via EDM T1 which should contain ECL amount tagged with stage values(1,2,3) | Rubicon - IFRS 9 EDM BSD v0.4.docx - 3. The Solution | Day 2 | NA |  | Refer to link in comment | [13 empty] | ECL calculations to RAH via T1 extraction | IFRS 9 Classification & Measurement Compliance IFRS 9 Group ECL Accounting | RFIFRS-49545 |  |  |  | 7 | 7 | 0 | 0 | 0 | 0 | 0 |  | Job run - RAH pull ECL TRD data from EDM. | 7 | 0 | 0 | 0 | 7 | 0 | 0 |  | Job run - RAH pull ECL TRD from EDM.
[26 empty] | RFIFRS-49546 |  |  |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 |  | Table row count to confirm data pulled from EDM to RAH. Verifying Rule,Trd Source tbl, GL Cob date tbl, Writeback Hist tbl, Writeback src type tbl. TP: EBBS | 4 | 0 | 0 | 0 | 4 | 0 | 0 |  | Table row count to confirm data pulled from EDM to RAH. Verifying Rule,Trd Source tbl, GL Cob date tbl, Writeback Hist tbl, Writeback src type tbl. TP: KEDW
4 | RFIFRS-49459 | RAH feed to PSGL containing provision and impairment data for posting | IFRS 9 EDM BRD v1 13 Scope 1 2.docx -2.2 Scope Statement | RFIFRS-49461 | 1) ECL results sourcing 2) ECL population run through BRE to generate DR CR 3) Chartfield stamping and journals & balances generation 4) Posting to PSGL based on accounting rules (engine) setup | Rubicon - IFRS 9 EDM BSD v0.4.docx - 3. The Solution | Day 2 | NA |  | Refer to link in comment | [13 empty] | EDM write back (ECL Accounting) : BRE enhancements for ECL calculations PSGL postings of the ECL calculations via RAH | IFRS 9 Classification & Measurement Compliance IFRS 9 Group ECL Accounting | RFIFRS-49998 | Y | N | NA | 2 | 0 | 0 | 0 | 0 | 2 | 0 |  | Finance - Verify 2 files from RAH Note: Based on the program delivery timelines, RAH to PSGL posting will not be part of Day2 SIT. It is deferred from SIT to UAT Day2 | 2 | 0 | 0 | 0 | 0 | 2 | 0 |  | Finance - Verify 2 files from RAH Note: Based on the program delivery timelines, RAH to PSGL posting will not be part of Day2 SIT. It is deferred from SIT to UAT Day2
[26 empty] | RFIFRS-49547 |  |  |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 |  | Job run - BRE enhancement & PSGL posting. Preparing View 5 (TRD Impairment) | 4 | 0 | 0 | 0 | 4 | 0 | 0 |  | Job run - BRE enhancement & PSGL posting. Preparing View 5 (TRD Impairment)
[26 empty] | RFIFRS-49548 |  |  |  | 4 | 2 | 2 | 0 | 0 | 0 | 0 |  | Table row count -2 Tcs - View 5 ( Trd Impairment), 2Tcs added from Cycle 11 to retest defect RFIFRS-58482 (TANDEM). Tps: EBBS, TANDEM 2Tcs Failed - Retest Defect RFIFRS-58482 | 4 | 0 | 0 | 0 | 4 | 0 | 0 |  | Table row count -2 Tcs - View 5 ( Trd Impairment), 2Tcs added from Cycle 12 to retest defect RFIFRS-58482 (TANDEM). Tps: KEDW,TANDEM
5 | RFIFRS-49468 | Consolidated adjustment to be feed for ECL calculation post filtering and review. | IFRS 9 EDM BRD v1 13 Scope 1 2.docx -2.2 Scope Statement | RFIFRS-49470 | 1) Consolidation of Adjustments performed - combination of TP GL recon, Exposure balances adjustments and Reclassification of IFRS9 | Rubicon - IFRS 9 EDM BSD v0.4.docx - 3. The Solution | Day 2 | [16 empty] | Not delivered as part of Drop1 and Drop2
6 | RFIFRS-49444 | Accounted exposure balances with accounting classification for ECL calculation | IFRS 9 EDM BRD v1 13 Scope 1 2.docx -2.2 Scope Statement | RFIFRS-60066 | 1) Sourcing of TP balances with (or without) GL chartfields at the granular level (trade/position/loan/card) 2) IFRS 9 classification (using Trade data attributes, portfolio mapping) 3) IFRS9 classification using COA chartfield 4) Reconciliation between two methods 5) Exposure accounting categorisation stamping 6) Exposure views and other assets, Charge off views 7) Detail row level Reporting views | Rubicon - IFRS 9 EDM BSD v0.4.docx | RAH PR5 REGRESSION | NA | Y |  | RFIFRS-60066 | [12 empty] | Accounting classification tagging for all inbound trades, Exosure accounting categorisation tagging for trades and Accounted balances by source views available in RAH T3 for extraction to ECL | IFRS 9 Classification & Measurement Compliance | RFIFRS-60066 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 768 | 0 | 0 | 0 | 768 | 0 | 0 |  | Control-M jobs run: - Day2 job related to processing Trade, ASL categ, GLSRC view TP: HOGAN MARCIS TANDEM T24 RFAS RLS CCMS SCILL KEDW EBBS
[30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 63 | 0 | 0 | 0 | 63 | 0 | 0 |  | Row count validation for tables inserted with data after job run TP: HOGAN MARCIS TANDEM T24 RFAS RLS CCMS SCILL KEDW EBBS
| RFIFRS-49456 | ECL feed to RAH containing provision data and stage information |  |  | 1) ECL writeback to RAH via EDM T1 which should contain ECL amount tagged with stage values(1,2,3) | [18 empty] | ECL calculations to RAH via T1 extraction | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 12 | 0 | 0 | 0 | 12 | 0 | 0 |  | Job run - RAH pull ECL TRD & GL data from EDM.
[30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 25 | 0 | 0 | 0 | 25 | 0 | 0 |  | Table row count to confirm data pulled from EDM to RAH. Verifying TRD & GL Source tbl, GL Cob date tbl, Writeback Hist tbl, Writeback src type tbl.
| RFIFRS-49459 | RAH feed to PSGL containing provision and impairment data for posting |  |  | 1) ECL results sourcing 2) ECL population run through BRE to generate DR CR 3) Chartfield stamping and journals & balances generation 4) Posting to PSGL based on accounting rules (engine) setup | [18 empty] | EDM write back (ECL Accounting) : BRE enhancements for ECL calculations PSGL postings of the ECL calculations via RAH | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6 | 0 | 0 | 0 | 6 | 0 | 0 |  | Job run - BRE enhancement & PSGL posting. Preparing View 5 (TRD Impairment) & View 6 (GL Impairment)
[30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 23 | 0 | 0 | 0 | 23 | 0 | 0 |  | Table row count - 21 Tcs - View 5 ( TRD Impairment) & View 6 ( GL Impairment)
[30 empty] | 637 | 633 | 2 | 0 | 0 | 2 |  |  |  | 60 | 20 | 1 | 0 | 37 | 2
Note on K11: 1438122: http://teamsites.sc.com/sites/finance/gfs/edm/SCB%20Group%20Finance%20Document/Forms/AllItems.aspx?RootFolder=%2Fsites%2Ffinance%2Fgfs%2Fedm%2FSCB%20Group%20Finance%20Document%2F16001462%20%2D%20IFRS%209%20Risk%20and%20Finance%20Delivery%20%2D%20EDM%20%28Phase%203%29%2FRubicon%20Accounting%20Hub%2F05%20%2D%20Code%20and%20Unit%20test%2FIFRS9%20UNIT%20TEST%20RESULTS&FolderCTID=0x0120005D573510FC817C429CA3B27C8C801307&View=%7B2916DEC4%2D7EB7%2D46DA%2D8E44%2D321DA65DD66C%7D&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence
Note on K12: 1438122: http://teamsites.sc.com/sites/finance/gfs/edm/SCB%20Group%20Finance%20Document/Forms/AllItems.aspx?RootFolder=%2Fsites%2Ffinance%2Fgfs%2Fedm%2FSCB%20Group%20Finance%20Document%2F16001462%20%2D%20IFRS%209%20Risk%20and%20Finance%20Delivery%20%2D%20EDM%20%28Phase%203%29%2FRubicon%20Accounting%20Hub%2F05%20%2D%20Code%20and%20Unit%20test%2FIFRS9%20UNIT%20TEST%20RESULTS&FolderCTID=0x0120005D573510FC817C429CA3B27C8C801307&View=%7B2916DEC4%2D7EB7%2D46DA%2D8E44%2D321DA65DD66C%7D&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence
Note on K14: 1438122: http://teamsites.sc.com/sites/finance/gfs/edm/SCB%20Group%20Finance%20Document/Forms/AllItems.aspx?RootFolder=%2Fsites%2Ffinance%2Fgfs%2Fedm%2FSCB%20Group%20Finance%20Document%2F16001462%20%2D%20IFRS%209%20Risk%20and%20Finance%20Delivery%20%2D%20EDM%20%28Phase%203%29%2FRubicon%20Accounting%20Hub%2F05%20%2D%20Code%20and%20Unit%20test%2FIFRS9%20UNIT%20TEST%20RESULTS&FolderCTID=0x0120005D573510FC817C429CA3B27C8C801307&View=%7B2916DEC4%2D7EB7%2D46DA%2D8E44%2D321DA65DD66C%7D&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence